# IQP Project Management Guide

TABLE OF CONTENTS

IQP Project Management Guide	1

ALIASES, EMAIL ETIQUETTE AND FILE NAMES	3

ALIASES	3

EMAIL ETIQUETTE	3

FILE NAMES and DOCUMENT HEADERS	3

PROJECT MEETINGS	4

GENERAL INSTRUCTIONS	4

Meeting Secretary (or Recorder)	5

The first meeting among yourselves	5

Some General Advice Regarding Meeting With Your Partners	5

AGENDA	6

Agenda For First Meeting With Advisors	6

MINUTES	7

PROJECT LOG & PROJECT LIBRARY	8

PROJECT LOG	8

General Description	8

Project Log Contents	8

Project Log Submissions and Grading	8

PROJECT LIBRARY	8

TEAM TASK LIST	9

INTERNAL TEAM SCHEDULE	10

DOCUMENT FORMATTING REFERENCE	11

Identifying Information	11

Staples	11

Page Numbers	11

Margins	11

Line Spacing	11

Fonts	11

Headings	11

Figures	11

Tables	12

Captions	12

Cross-References	12

Citations and Footnotes	12

Final Proposal and Final Report	12

Report Formatting Summary	13

DRAFT SUBMISSION COVER SHEET	14

MISCELLANEOUS	15

IGSD Information and Forms for Projects Off-campus	15

Library assistance	15

# ALIASES, EMAIL ETIQUETTE AND FILE NAMES

## ALIASES

Please, create email aliases for your teams, using the following names:

ve09-orig@wpi.edu

ve09-post@wpi.edu

ve09-ships@wpi.edu

ve09-nomics@wpi.edu

ve09-move@wpi.edu

ve09-earth@wpi.edu

ve09-40@wpi.edu

Aliases can be created by going to: https://www.wpi.edu/Academics/CCC/Services/Email/mailinglist.html

These aliases should contain ONLY the email addresses of the student members.  If you want to email the project advisors, add their email addresses in the CC field when you send messages out.

The groups inside my.WPI are useful, but when it comes to communicating with the outside world, like your liaisons, we need a "regular" address that reaches all of you.

You should ALWAYS address all your emails to the entire team (at least in the cc:) as well as to outsiders (including – when appropriate – your advisors).  This makes it easier for the respondent to reply to all your team.

We will use the aliases in our correspondence with the liaisons.

## EMAIL ETIQUETTE

Emails to sponsors and advisors should always be professional (clear and grammatically correct sentences), though you may be more informal with advisors than sponsors.

When you email your advisors, please copy the message to the alias group, so that we can reply to the whole group and not to just the student that sent the email to us (except when you wish to communicate privately with your advisors).

Always put your team's "nickname" in the subject followed by a colon and then put a "meaningful" subject.  For example:

Origin: Draft of Introduction

Move: Assignment #3

Veninomics: question

Postmortem: meeting request

## FILE NAMES and DOCUMENT HEADERS

When you create any files from now on and then attach them to messages, always start with a meaningful primary descriptor, followed by an underscore, then the term, underscore again, and ending with your team's short name.  Use underscores instead of spaces (makes it easier later when we put stuff on the web).  Here are some examples:

Proposal_ B09_Mobility.doc

Report_B09_Publicearth.doc

Survey_List_B09_Venice40.xls

Always include your team’s full name or nickname IN THE HEADER inside the document as well.

We recommend you use the document’s First Page Header for that purpose.

# PROJECT MEETINGS

## GENERAL INSTRUCTIONS

Every team will meet with the advisors once a week.

Here are some ground rules for PQP meetings.  They will apply for project meetings when on site as well.  For more insights, take a look at The Manager's Guide to Effective Meetings by Barbara J. Streibel or to other books like it.  You will find plenty of useful suggestions about meetings in there, but you need to adapt some of the advice to the project environment since most of these books are aimed at businesses.

The IQP is a learning experience in several dimensions. One of these is a professional dimension. You will be working with professionals in the city, and we expect you to learn how to properly function in a professional environment.

- Arrive on time. Please let your team members or advisors know in advance if you have to miss a meeting for legitimate reasons.

- Be prepared. This includes completion of weekly tasks and writing assignments.

- Bring an agenda. Agendas typically include weekly accomplishments, questions or issues needing attention, and plans for the upcoming week.  More on the Agenda below.

- Bring the Team Task List. More on the task list later in this document.

- Run the meeting. One team member will act as a meeting chair and will control and coordinate the proceedings (on a rotating schedule).

- Take minutes. At least one person should do this, and you should rotate minute-taking duties for each meeting. Moreover, each person could also take notes and the team later combines them into one set of minutes.  Minutes are typed up and sent to advisors (and sponsors when on site) by the next business day.  More on Minutes below.

- Dress properly. For PQP meetings this means normal attire for attending classes, except please remove outerwear and all caps and hats. For sponsor meetings, attire will include business dress appropriate for the agency. Usually this is a collared shirt and tie for the men and business suit for the women (with appropriate shoes in each case---no sneakers).

- Do your “homework”.  Remember that ID 2050 + PQP = 1/2 unit, and 1/2 unit = 25 hours/week per person.  Since you will only be in classes and meetings with us about 5 hours/week, this means that each person will need to put in about 20 person-hours of outside work the project each week.  We'll be looking for evidence of this in our meetings.  Some of this time MUST be spent meeting and communicating with your teammates for things to go smoothly.

- Bring Evidence of your work . Plan to attach a packet of information to the agenda every week to demonstrate what you’ve done and to prepare the discussion.  Keep the packet brief and to the point.  No need to swamp the advisors with paper if it’s not digestible at a glance.

- You should use the same format and procedures for all meetings you have among yourselves

- Meetings schedules will be arranged at start of classes

- Additional times will be set up as needed.

## MEETING STRUCTURE

We recommend adopting the sociocratic principles in the running of at least some parts of our meetings.

The team should read up the information at the above link, as well as on Wikipedia, and determine when and to what extent the meetings should involve some elements of Sociocracy.

Every meeting should follow the following structure:

- Every meeting will be conducted by a student acting as the meeting chair person

- The Agenda for every meeting will be sent ahead of time and copies will distributed to all attendees at the start of the meeting

- A secretary will record the proceedings and will produce a transcript of the advisors’ feedback and a list agreed tasks, to be reviewed at end of meeting

- The meeting will start with a review of the team’s actions in response to last week’s advisor feedback

- Then the team will review the week’s accomplishments which will be based in part (but not exclusively) on last week’s agreed task list

- The team will distribute copies of the weekly group assignment to each advisor and will review the assignment

- The team will then have a chance to discuss any topic of its choice in order to get additional feedback

- If needed, policy rounds could be included in the meeting and approved by consent

- The student can then lead the discussion on other miscellaneous issues of their choice

- In the last 5-10 minutes of the meeting, the secretary will read the essential elements of the advisors’ oral feedback, which will be officially approved by consent

- Likewise, a weekly task list, above and beyond the following group assignment will be agreed upon

- Copies of the advisor feedback and task list will be made and retained by students and advisors

### Meeting Chair

The weekly meeting chair will be in charge of ensuring that the meeting achieves all the desired objectives within the allotted time.  The student in charge will:

- move the meeting through the above 12 steps and

- make sure that all of the items in the agenda are adequately addressed during the meeting.

- mediate any sociocratic rounds that the team deems necessary to arrive at consent on specific policies or issues.

### Meeting Secretary (or Recorder)

- One team member will act as a meeting secretary and will record the proceedings (on a rotating schedule)

- The secretary will produce the meeting’s AGENDA before the meeting (see below) and then write-up the MINUTES at the end of the meeting (see below).

- Agendas and Minutes will be archived weekly in the log notebook (see separate section about PROJECT LOG)

- The secretary will be responsible for logging all ORAL feedback from the advisors and will produce a record of the main feedback points before the end of the meeting, so that the essence of the feedback is agreed upon, copied and archived.

- Similarly, the secretary will also develop a list of tasks that will also be reviewed at the end of the meeting, copied and archived.

- A different person will then become responsible for the following week’s meeting AGENDA, RECORDING and MINUTES

- The next meeting will start with a review of the accomplishments based on the prior week’s advisor feedback and on the agreed upon task list (which should be augmented by the team every week).

- The performance of each student as the secretary will be noted and will count toward the final grade

## MEETING WITH YOUR PARTNERS

- It's important to realize that your partners are likely to have different styles of working and interacting with others than you do.  Try to be aware of your own style and openly seek ways to work together.  Diversity is a strength in project work--it usually makes for better results--but it also makes the teamwork more challenging.

- If some team members already know each other well, it's important NOT to have meetings by yourselves about the project, especially before the team is able to meet about a particular issue.  Do your best to save your ideas for when all of you are together.

- Rotate who runs the meetings among all  partners.  Not everyone is equally eager or experienced in doing this, but it's important that everyone has chances to do this. (We'll be expecting you to do this in meetings with us.)

- Be careful to rotate other tasks, such as note-taking, research, etc., among all partners. Don't fall into the roles you're most comfortable with unless everyone has agreed on it. Avoid roles based on gender, whether out in the field, or in meetings.

- Adopt the Sociocratic Principles when running your meetings.  Make certain that all members get time to voice their opinions and ideas.  Don't let anyone dominate the discussion.  It is VERY hard for extroverts to learn to SHUT UP long enough to let other people have time to think through and voice their ideas.  Extroverts like to think aloud, and actually start talking before they know what they’re going to say.  Consequently, they are always ready to say something BEFORE other people, and are also more fond of having the floor than others.  The results aren't good unless we learn to make a point to hear from those who aren't as quick to voice opinions.  Their ideas are often much better thought out!

- When there are reasons for the team to break into twos – and there will be many times during prep and the project when this makes sense – be sure to split yourselves up in varied ways, especially at the beginning.

- Schedule meetings in locations that are convenient and comfortable for all members.  Meeting on "neutral turf" somewhere on campus might be most effective.

### The first meeting among yourselves

Here is a guide for your first team meeting (without advisors):

- Introduce yourselves, and get to know each other a little.  It's a good idea to go around the room and talk about how each of you is feeling about the project and the entire prospect of going off-campus for your IQP.

- Exchange information (telephone numbers, IM addresses, etc.).  Talk about preferred modes of communication; you need to know if your partners are "e-mail people" or not, for example.  Make sure you check YOUR email frequently.

- Discuss your schedules for the term, and some meeting strategies.

## AGENDA

The project team has the responsibility to run weekly meetings.  The progress report /agenda for each meeting should always include the following items:

- Project Mission and Objectives.  It is very useful to keep the project’s mission and objectives listed at the top of your agenda every time you meet with the advisors (or with anybody else).  This will act as a constant reminder of why you are meeting and will also be an opportunity to revise and hone the mission and objectives from week to week.

- Accomplishments in the previous week. Instead of just providing a laundry list of topics or tasks, really try to make your report informational, so that it has some take-away value. What specifically did you learn? What major issues emerged? What key resources did you find? Where appropriate, include attachments as part of an agenda “packet” in order to provide more information. Do not list “trivial” accomplishments such as sending an e-mail, making a telephone call, etc., nor should you list obvious, routine things such as going to meetings and classes.  Focus on substantive accomplishments of interest to the attendees, and especially on the outcome of your efforts.

- Topics to be discussed at meeting.  The agenda should set the tone for the meeting.  It should contain a list of items to be discussed, both related to project logistics, as well as to content.  A bulleted or numbered list will suffice.  Be specific in your items list.  Do not use generic headings.  If you want to group discussion items into larger heading, do so, but make sure that the specific topics to be discussed are listed.  .

- Plans for the next week. Again, focus on substantive plans and what you intend to accomplish by the next meeting. Be specific, and include who will be doing what.

Another way to gauge the appropriateness of these agenda items is to ask yourselves if the content reflects the level of expected effort (outside of class) for a one week period, which is about 80 hrs/team! Are the outcomes of about 80 hours evident?  Remember that each team member should participate in every meeting, with responsibility for some subset of the agenda items. The chair’s role is to keep the meeting on track, not to report everything himself or herself.

- The agenda should fit on a single page.

- Unfinished tasks from last week should be moved to the “action” list for the current week.

- The secretary must send the AGENDA to the team alias and to the advisors by NOON the day before the meeting.   The mailing must follow proper email etiquette.

- The secretary must bring enough copies of the AGENDA to the meeting.  Each advisor will get a copy and one copy will be for the team.

### Agenda For First Meeting With Advisors

The advisors will produce the FIRST agenda.  After the first meeting you will be in charge.

Here’s an example of an agenda.  More examples of past student agendas are available on line.

## MINUTES and NOTES

As mentioned, the main focus of the secretary during the meeting is to distill the essential elements of the advisors’ oral feedback and the meeting’s task list.

The secretary and everyone else on the team should also take notes about all other discussions that occur during the meetings, and all team members should coordinate with the secretary to compile the minutes soon after the meeting took place.

- The minutes should start with the meeting date and start and end times as well as the people in attendance.

- The secretary’s name should be indicated at the top of the minutes.

- The minutes should then contain a header for each main discussion topic on the agenda (we suggest cutting and pasting the agenda topics into the minutes as a basis for this part of the minutes)

- Each agenda header should be followed by one or two sentences under each topic to summarize the discussion.  Make sure you keep track of whatever conclusions were reached, as well as loose ends.

- The minutes should end with the weekly advisor feedback transcript and with the weekly task list.

  - Tasks should be assigned to specific people.

  - Deadlines should be placed on tasks assigned.

Here are some important items regarding note-taking during project meetings with the advisors:

- Advisors usually get annoyed when they participate in project meetings in which no student is writing anything.

- Taking notes shows commitment and a good attitude toward the project---the kind of things that help students earn better grades.

- Although some advisors can be accused of talking just to hear themselves talk, most of what we offer is meant to help the group and is worth recording.

When minutes read like: "Discussed improvements to next draft", that's not helpful.  A better example might be something like:  "Discussion on background research included:

- contact Prof. XX about (topic)

- check library at Univ. of YYY for  reference on (topic)

- investigate use of focus group methods for objective 3

The secretary must send the MINUTES to the team alias and to advisors by NOON the day after the meeting.  The mailing must follow proper email etiquette.

Examples of past student Minutes are available on line.

KEEP IN MIND THAT THIS YEAR WE ARE INTRODUCING NEW FORMATS so the online examples do not conform to these new directives.

Consult the book (The Manager's Guide to Effective Meetings by Barbara J. Streibel) for more guidance.

## ADVISORS’ ORAL FEEDBACK TRANSCRIPT

The primary (if not exclusive) mode of feedback that the team will receive from the two advisors will be oral.  During any meeting with the advisors, a secretary will capture the essence of all of the advisors’ oral feedback and will recapitulate all of the main suggestions and critiques before the end of the meeting.  The reviewed and agreed transcript of the advisors’ feedback will be attached to the meeting minutes.

## MEETING TASK LIST

At the end of a meeting we will typically ask: "So what will you do this week?"  When there has been little or no note-taking, the response is usually "Uh, I guess we'll….OK……uh,…I didn't write it all down", or "We're going to do all the things we just talked about."  Neither response is acceptable, hence the requirement for the task list before the end of the meeting.

- Make sure you tag each action item with the name of one or more team members who will be responsible for carrying out that task.

- Make sure you put a deadline next to each action item as well.

- At the next meeting, the people responsible for each action item should have specific results that directly relate to each item.

Note that follow-up can mean providing a valid reason for rejecting a suggestion. For example: "Joe contacted Prof. XX and she told him that…(topic)….wasn't important in this problem, so we don't need to worry about it", is way better than "Oh, we forgot you suggested to contact Prof. XX.----We'll do it this week."

The most frequent reason the latter answer is given is because no one wrote down the suggestion during the meeting.

# PROJECT LOG & PROJECT LIBRARY

Due: 	Ongoing, brought to every team gathering, beginning with the first PQP meeting

Purpose: 	Develop research project management skills by maintaining an organized reference file of all project-generated documents, including meetings documents, assignments, team decisions (e.g., norms, task responsibilities, etc.), faculty feedback, etc.

## PROJECT LOG

### General Description

- Every team will be required to keep a “Project Log”, using a 4”, 3-ring binder.

- The team must keep the Project Log up-to-date and bring it to every team meeting.

- It will be a repository for everything that each team produces in the course of the PQP

### Project Log Contents

The Project Log will contain 7 tabbed dividers to separate each week’s information and each weekly section will in turn contain the following items, more or less in this order:

- Current “Team Task List”: A running log of all project-related team and individual tasks, indicating what, when, who and status of each task.

- PQP meetings: All agendas & minutes of weekly PQP meetings and any other meetings with faculty

- Summaries of the main contacts, meetings, interviews, letters or emails for the week

- All assignments due that week

- All returned assignments, drafts or other work commented on and returned by faculty

- Any team-dynamics issues that emerged during the week

- Anything else that is of importance to the project and was collected or produced that week

If one notebook should prove not to be enough, add others as needed.

### Project Log Submissions and Grading

- The Project Log should be brought to every PQP and team meeting. The log will be reviewed and graded occasionally by the advisors.

## PROJECT LIBRARY

The Project Library should contain project-relevant research articles, brochures, web page printouts, books, sponsor information, and other documents investigated as part of your project. Wherever practical, keep full copies of important articles, etc. for later reference. Purchase or arrange to borrow books you will need to have on-site. Keep documents in a 3-ring binder and\or other appropriate container. Maintain an annotated bibliography of materials in the Project Library as a table of contents.

# TEAM TASK LIST

Each team must create and regularly update a Team Task List. Such a list is essential for keeping track of and knowing who and when various activities need to be accomplished. Below you see a sample spreadsheet you may wish to use (you can download this from our online handouts page), or create one of your own. Assignments and suggestions made by advisors in class and PQP should be added to the Task List, as should all team-initiated tasks. Use the Task List as a reference in your team-only meetings and bring hardcopies of the current Task List to all PQP meetings. You may assign the weekly PQP secretary to update the Task List, or have this be an ongoing responsibility for one individual. Either way, all team members share responsibility for staying on schedule and completing and communicating task status to whoever is managing the weekly Task List.

Sample: Information incomplete and not necessarily accurate – check all!

| Team Task List: Parking Study |  |  |  | Last updated: | 1/12/2005 |
| --- | --- | --- | --- | --- | --- |
| What |  | When | Who | Status | Notes |
| Submit Project Preference form |  | Th 1/13, noon | All | done |  |
| From "Project Management" packet |  |  |  |  | Review packet together, assigning responsibilities |
| PQP secretary (week 1): minutes |  | W 1/19 | Ozzie |  |  |
| PQP Log & Library (buy & set-up) |  | W 1/19 | Ozzie |  |  |
| Team meeting schedule form |  | Su 1/22 | Team |  |  |
| PQP registration |  | W 1/19 | All |  |  |
| Contact librarian |  | Su 1/22 |  |  |  |
| Review document formatting & check that first papers comply |  | Su 1/22 | All |  |  |
| Grading memo: read |  | M 1/17, class | All |  |  |
| "Sample Proposal" assignment |  | M 1/17, class | All |  |  |
| "Library Tutorials" assignment |  | W 1/19 & Sa 1/29, 9:00AM | All |  |  |
| Team Task List: set-up and update |  | W 1/19 PQP, then ongoing |  |  | Create 1 list for team use, and individuals may wish to create their own. |

# INTERNAL TEAM SCHEDULE

Project Title:_________________________________________________________________

Instructions:  In the table below, please indicate the time slots when you will meet as a team outside of the ID2050 and PQP meetings.  Bring this to the first PQP meeting.

|  | Mon | Tue | Wed | Thu | Fri | Sat. | Sun. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8:00 |  |  |  |  |  |  |  |
| 9:00 |  |  |  |  |  |  |  |
| 10:00 |  |  |  |  |  |  |  |
| 11:00 |  |  |  |  |  |  |  |
| 12:00 |  |  |  |  |  |  |  |
| 1:00 |  |  |  |  |  |  |  |
| 2:00 |  |  |  |  |  |  |  |
| 3:00 |  |  |  |  |  |  |  |
| 4:00 |  |  |  |  |  |  |  |
| 5:00 |  |  |  |  |  |  |  |
| 6:00 |  |  |  |  |  |  |  |
| 7:00 |  |  |  |  |  |  |  |
| 8:00 |  |  |  |  |  |  |  |
| 9:00 |  |  |  |  |  |  |  |
| 10:00 |  |  |  |  |  |  |  |

# DOCUMENT FORMATTING REFERENCE

For IQP proposals, reports, drafts & most other documents

## Identifying Information

Always put your NAME(S), TEAM, ASSIGNMENT TITLE and identify for each section the lead AUTHOR and REVIEWER, using the Draft Submission Cover Sheet (for short individual or team assignments, you can skip the Cover Sheet and put the information on the first page of the document).

## Staples

All documents must be stapled (or clipped, if too thick to staple).

## Page Numbers

All pages MUST be numbered from day one (i.e., from the very first draft of the very first chapter).  Word will number the pages automatically, so use this feature.  Page numbers should appear at the bottom of the page (RIGHT or CENTER).  Consider Garamond 12pt. as a font for the page number.

## Margins

The final document should have margins of 1” on Top, Bottom, Right and Left.

## Line Spacing

Finished PQPs should be spaced using 1½ line spacing.

## Fonts

When printing, one could use several fonts, however we suggest Garamond 11 Pt. or Times New Roman 12 Pt. as the default "Normal" font.

## Headings

All sections should be preceded by proper headings.  Always use the “Heading 1”, “Heading 2”, etc. styles in Word. You may use a fourth level (“Heading 4”), but you should not go beyond four levels of headings.  Heading numbers are optional.  See the Report Formatting Summary Table below for suggested heading style formats.

## Figures

Your report will contain numerous illustrations.  Whether these are photos, graphs, charts or diagrams, they are all going to be called FIGURES.  You should adhere to the following guidelines:

- As much as possible figures should be incorporated into the text and not placed on separate pages (this rule is less important in early drafts).

- The reader should be allowed to view the figure and the accompanying text simultaneously whenever possible.

- Full-page copies of the most important graphs could be placed in a special appendix referenced in the document’s body near where the smaller version will be inserted.

- The sources of figures that were not produced by your team should be referenced.  This could be done with footnotes at the bottom of the individual pictures or on a separate page, either at the end of each chapter or at the beginning/end of the entire PQP.

## Tables

Your report will also likely contain information in TABLES (data in rows and columns).  Tables are generally labeled separately from FIGURES, but should be presented in keeping with the rules for FIGURES, and

- Avoid tables that “break” across pages (i.e., are not all on one page), unless absolutely necessary.

## Captions

- Each illustration should be accompanied by a “Caption” inserted right below it, and centered.

- To insert a caption select "Insert - Caption" in Word.  This will guarantee that the captions will be automatically numbered and the List of Figures can be automatically produced.

- For all captions, we suggest using an Arial Narrow font, 10 points, not Bolded.

- You may need to use a Frame to place the illustration where desired and to let the text of the document flow around the illustration.

## Cross-References

- All graphs, Tables and Figures should be referenced in the text and each should be numbered.

- References should be made by figure/table number and optionally by page, but never by page alone.

- The preferred numbering system is to use a combination of Chapter number and figure number, such as Fig. 6-12, i.e. the 12th figure in chapter 6.  This makes it easier to put together the PQP without worrying about the numbering being dependent on previous unfinished chapters.  However, simple, continuous numbering is OK too.  Most word processors have an automatic numbering feature, use it!

## Citations and Footnotes

- All material, data, and concepts that do not originate from your fertile minds should be referenced clearly. This applies to quotes (which should be quoted) as well as to generic concepts or ideas derived from outside sources. Details will be covered in class.

- Occasionally, there may be a word or a concept in the text that needs some explanation.  In this case, a footnote is also in order at the bottom of the page, to explain the meaning of the word or to expand on the concept.  A Glossary of terms could be included in one of the Appendices to explain all project-specific terms that appear frequently in the text.

## Final Proposal and Final Report

Special instructions for final proposals and reports will be provided later.

## Report Formatting Summary

| Item | Specification | Notes |
| --- | --- | --- |
| Margins | 1" | All (Top, Bottom, Right and Left) |
| Line Spacing | 1 ½ |  |
| Heading Style Formats (recommended) |  |  |
| Normal Font | Garamond, 11pt |  |
| Heading 1 | ARIAL 14, ALL CAPS, BOLD |  |
| Heading 2 | Arial 12, Bold |  |
| Heading 3 | Arial 11, Underlined |  |
| Captions | Arial Narrow 10 | Centered under figure/table |

# DRAFT SUBMISSION COVER SHEET

(submit with each written assignment)

Document Title:		_________________________________

Team/Project Name:	_________________________________

Date submitted:		_________________________________

Edited by:			_________________________________

| Sect. # or Name | Written by | Reviewed by | Major Changes? | NOTES |
| --- | --- | --- | --- | --- |

OVERALL NOTES:

(use back of sheet if necessary)

# MISCELLANEOUS

## IGSD Information and Forms for Projects Off-campus

Please visit and remember www.wpi.edu/Academics/Depts/IGSD/Student/ as a key source of information on WPI policy and “how-tos” concerning laptops, cell phones, travel documentation, etc.

## Library assistance

Reference Librarians will help you learn how to find essential information (journal articles, government reports, newspaper articles, etc.) for your project during both the preparation and on-site phases of your work. They can be enormously helpful to you.  You will receive instructions and assignments regarding the library research process.